## Sheet1
The Engineer Accelerator September 2016
Deliverables Tracking
Assigned
2016-09-17 | Due | Time | Notes
Estimate the number of hours it will take to complete the Product Definition | 2016-09-17
Feature Block Diagram | 2016-09-21 | By Class Time
Product Definition.txt | 2016-09-21 | By Class Time
2016-09-24
Enter the total hours it took to complete the Product Definition | 2016-09-24 | by the end of class
Estimate the hours to complete Realization | 2016-09-24 | by the end of class
Estimate the hours to complete the Architecture | 2016-09-24 | by the end of class
Major Components BOM | 2016-09-26 | End of Day. | I will order parts on Monday to make sure they are in house by Saturday. If you do not get me the parts order by then you may not be able to build you project.
Enter the total hours it took to complete the Architecture | 2016-09-28 | By Class Time
Hardware Block Diagram | 2016-09-28 | By Class Time
Product Architecture | 2016-09-28 | By Class Time
Eagle Library | 2016-09-30 | By Noon
Eagle Schematic | 2016-09-30 | By Noon | ERC Cleared
Eagle Layout | 2016-09-30 | By Noon | DRC is cleared
Cable Definition (if cables are needed in your design) | 2016-09-30 | By Noon
Feature and Behavior Acceptance criteria | 2016-10-01 | By Class Time
2016-10-01
Enter the total hours it took to complete the Realization | 2016-10-01 | By end of class
Estimate Hours for Full BOM, Manfucaturing Package, and Bring Up | 2016-10-01 | By end of class
Board Bring Up | 2016-10-05 | By class time
Board Fab and Build | 2016-10-01 | By end of class
Full BOM | 2016-10-07 | By Noon
Manufacturing Package | 2016-10-07 | By Noon