## Sheet1
Author | Malcolm Knapp
Date | 2016-09-22
Project | Arduino Kiln
Product Definition
Version | Reviewer | Document | Issue | Suggestion | Documentation Updated
0.1 | Malcolm Knapp | Feature Block Diagram | No Block Diagram. | The Product Definition is not complete without so you will need to make it. All features in the feature list must appear in the block diagram | Done
0.1 | Malcolm Knapp | Product Definition | Device Characteristics--> Internal Dimensions? | Determine what these need to be | Done
0.1 | Malcolm Knapp | Product Definition | "Thermocouple Sensor" confusing name for this feature since the thermocouple itself is a sensor. What does the block do? | Make this a more accurate name. Maybe Signal Processor or Amplifier would be better. | Done (Thermocouple Amplifier – ThermAmp)
0.1 | Malcolm Knapp | Product Definition | Information that is listed under Interface are behaviors of the system. "On" is a state and "user adjusts temp" and "new temp not changed for 5s" are events within that state | Merge these into the behavior section.
0.1 | Malcolm Knapp | Product Definition | "Selector knob (or arrow buttons)" What does this select? Tempearture? | Choose knob or arrow button. If this does change the temperature then maybe change this to Temperature Knob/Arrows | Changed – now simple Start button
0.1 | Malcolm Knapp | Product Definition | Indicator Lights --> Power light is another color such as green or blue | Choose one or the other | Done
0.1 | Malcolm Knapp | Product Definition | Operational Requirements and Device Characteristics are talking about the same thing | Operational characteristics can be merged with Device characteristics. This will also reduce the redundancies.
0.1 | Malcolm Knapp | Product Definition | Missing Feature vacume pump? |  | Will address later, after consideration
0.1 | Malcolm Knapp | Product Definition | Missing feature neon source? |  | “
0.1 | Malcolm Knapp | Product Definition | What feature handles timing the 20minute soak time? Where does this characteristc go? |  | This will be programmed into the Arduino and not change without a computer.
0.1 | Malcolm Knapp | Product Definition | Notes at the can be marked as future features | Adjust as needed | Done
0.1 | Malcolm Knapp | Product Definition | Question marks need to be resolved | Before the product definition is complete the unknown information should be determine and the queston marks removed | Done
0.1 | Malcolm Knapp | Product Definition | Missining Characteristic: Thermocouple Temp range? |  | Not sure – scavanged from a furnace that goes hotter than my kiln will need to go
0.1 | Malcolm Knapp | Product Definition | Nichrome heating element Temp range characteristic??
0.1 | Malcolm Knapp | Product Definition | Uses mains power, 10’ cord -What uses mains power? |  | Removed
0.1 | Malcolm Knapp | Product Definition | Missing State: Cooldown? After the heater is turned off how does the user now when it is safe to open the kiln door and take out the tube? |  | Added behavior: Start button starts the firing schedule. The kiln tells you when it's ready to process the electrode. Then press Start again to cooldown.
PCB
0.1 | Malcolm Knapp | Schematic | 1kohm limiting resistors on 7-segment display seems high. What is the current going through them |  | 25mA
0.1 | Malcolm Knapp | Schematic | Can you drive the SCR directly from the Arduino pin. How much current does it draw? Will you overdrive the SCR if it connected directly to the pin? Is there are special drive circuitry needed to interface to the SCR |  | It says “Minimum on voltage (controlled) = 3; Minimum on current (controlled) – 1.5m” Specs: http://www.americanmicrosemi.com/catalog/SC649000.html
0.1 | Malcolm Knapp | Schematic | What is the purpose of the 4.7kohm resistors on the transistor gates? |  | From the Adafruit website: “and then connect NPN transistors or a TPIC6B595 to the cathodes to sink the 8*20mA = ~120mA maximum per digit.”
0.1 | Malcolm Knapp | Schematic | Power indicator on 5V? You mentioned you wanted this but I do not see it. |  | This is the Power indicator – that the unit is plugged in
0.1 | Malcolm Knapp | Schematic | SPI signals are mislabeled. The standard is SCK, MISO, MOSI, and CS |  | Done
0.1 | Malcolm Knapp | Schematic | General: Value should be the part number for the component. If you want to add more information use the Attribute tool. Correct JP3. |  | Done
0.1 | Malcolm Knapp | Schematic | Make the color for LED1 an Attribute |  | Done.
0.1 | Malcolm Knapp | Schematic | Standard Reference Designator for Transistors is "Q" not "T" |  | Done
0.1 | Malcolm Knapp | Layout | The 5V signal connected to JP3.9 should be connected to the 5V pin on the Arduino. The VIN pin is for when you want to power the Arduino off something other that the USB. |  | Done.
0.1 | Malcolm Knapp | Layout | Consider making the bottom side of the board a ground plane. This will simplify your routing |  | Done.
0.1 | Malcolm Knapp | Layout | You can simplify the routing of the 7-Seg diplay by rotating it 180°. |  | Reassigned pins; solved.
0.1 | Malcolm Knapp | Layout | The standard packade for resistors is 1206 not 603 |  | Changed
0.1 | Malcolm Knapp | Layout | for the 7-seg you do not need to show diemensions |  | Changed
0.1 | Malcolm Knapp | Layout | For the spi traces if you come from the other side of the connector you will not have to change layers |  | Done
PCB Milling
0.2 | Malcolm Knapp | Schematic | Default Values for resistors and Capacitors are not displayed
0.2 | Malcolm Knapp | Schematic | Starter button not on schematic
0.2 | Malcolm Knapp | Schematic | Ready indicator not on schematic
0.2 | Malcolm Knapp | Schematic | Center Schemtic in middle of the frame
0.2 | Malcolm Knapp | Schematic | Find a frame that better matches the size of the circuit
0.2 | Malcolm Knapp | Schematic | Values not displayed on R1 - R11 | Display Values
0.2 | Malcolm Knapp | Layout | Thermocoule footprint has no component outline
0.2 | Malcolm Knapp | Layout | Headers for arduino shield come off the botton of the board | Move all traces on that connect to headers to the top side of the board
0.2 | Malcolm Knapp | Layout | Minor: Designer name and rev should be on the symbol layer not the net layer
Closure
0.2 | Malcolm Knapp | Feature Block Diagram | See Feature_Block_Diagram V02 Comments.pdf
0.1 | Malcolm Knapp | Hardware Block Diagram | See Hardware Block Diagram V01 Comments.pdf
0.1 | Malcolm Knapp | Major Components BOM | Title?
0.1 | Malcolm Knapp | Major Components BOM | Author?
0.1 | Malcolm Knapp | Major Components BOM | Version ?
0.1 | Malcolm Knapp | Major Components BOM | Project?
0.1 | Malcolm Knapp | Major Components BOM | Move all mechancial parts to the System BOM
0.1 | Malcolm Knapp | Major Components BOM | Move all minor parts to the full BOM
0.1 | Malcolm Knapp | Major Components BOM | Follow Major Components BOM template. I.e have columns for Voltage, Current, Tolerance, Wattage, Vendor, Vendor Part Number, Price, Qty≤ Manufacturer, and MFG Part Number
0.1 | Malcolm Knapp | Major Components BOM | F2-F4 are not readable | Update the formatting
1 | Malcolm Knapp | Major Components BOM | Make sure cell are big enough or use wrap text so no information is hidden and it is easy to read.
2 | Malcolm Knapp | Major Signal List | Thermocouple Amplifer max volatge is incorrect.
2 | Malcolm Knapp | Major Signal List | Ready Indicator signal. | Remove this if it is not used
2 | Malcolm Knapp | Major Signal List | AC signal is high power. Will you need disipation calculations for it?
2 | Malcolm Knapp | Major Signal List | Unamplified thermocouple signal is not shown. This is a small signal so noise impact should be consisdered
2 | Malcolm Knapp | Pinouts | It is unclear if 7-seg display pins 11-14 are connection to the SPI pins are th thermocouple amplifier is
2 | Malcolm Knapp | Pinouts | Add in pinout information for the USB, DC Jack, and AC connections
2 | Malcolm Knapp | Pinouts | Exapnd cells so no information is hidden
2 | Malcolm Knapp | Current Budget | Clearly separate AC and DC currents and totals
2 | Malcolm Knapp | Current Budget | Exapnd cells so no information is hidden
2 | Malcolm Knapp | Calculations | Display Resistor Results do not make sense | I think the Vf number is incorrect. Check the datasheet again and see if it has Forward Voltage information. If it does not find the generic Vf for blue LEDs